## CIP 2019 20K
PYC CAPITAL IMPROVEMENT PLAN 2019 - 2028 10 year plan - Very rough proposal 1/11/2019
| Life* | Estimate* | Annual | Replaced | Next | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | TOTAL
BUILDING
Carpet downstairs | 5 | 3500 | 700 |  |  | 2019: 3500 | 3500
Heating and air conditioning | 20 | 20000 | 1000 |  |  | 2023: 20000 | 20000
Paint dinning room, kitchen ceiling, flooring | 10 | 12000 | 1200 |  |  | 2020: 12000; 2027: 8000; 2028: 4000 | 24000
Plumbing replacement (need survey) | 25 | 10000 | 400 |  |  | 2024: 10000 | 10000
Replace kitchen floor & update kitchen | 10 | 20000 | 2000 |  |  | 2024: 8000; 2025: 12000 | 20000
Replace refrigerator unit in shed & kitchen | 15 | 4000 | 266.6667 |  |  | 2023: 4000 | 4000
Replace freezer in shed | 15 | 3000 | 200 | 2018 | 2033 | 2028: 3000 | 3000
Repair sliding windows | 10 | 2000 | 200 |  |  | 2019: 2000 | 2000
Replace roof | 30 | 20000 | 666.6667 | 2005 | 2035 | 2026: 35000 | 35000
Replace windows dining | 20 | 18000 | 900 |  |  | 2027: 10000; 2028: 8000 | 18000
Replace water heater | 10 | 3000 | 300 | 2019 | 2029 | 2019: 3000 | 3000
Replace 2 doors - (dining) repair siding | 25 | 5000 | 200 |  |  | 2021: 5000 | 5000
Sub structure inspection | 5 | 1000 | 200 |  |  | 2020: 1000; 2025: 1000 | 2000
Repairs to sub structure | 10 | 10000 | 1000 |  |  | 2020: 10000; 2021: 5000; 2022: 6000 | 21000
Replace tables and chairs | 10 | 5000 | 500 |  |  | 2021: 2000; 2022: 3000 | 5000
Update all club lighting | 10 | 6000 | 600 |  |  | 2025: 6000 | 6000
Upgrade WiFi system | 10 | 2000 | 200 |  |  | 2020: 2000 | 2000
4 Moorings in front of Club (staples) | 10 | 18000 | 1800 | [12 empty] | 18000
East sea wall | 25 | 25000 | 1000 |  |  | 2020: 25000 | 25000
North sea wall and pilings | 25 |  | 0 | [12 empty] | 2500
Carpet upstairs | 10 | 2500 | 250 | [12 empty] | 2500
LANDSIDE (no projections)
DOCK SYSTEM
Replace dock pilings (with north sea wall?) | 10 | 53000 | 5300 | 2015 | 2025 | 2025: 32000
Install sacrificial slide boards on 24 pilings | 10 | 4800 | 480 |  |  | 2019: 4800
Replace pier pilings, decking, walkway (swag) | 25 | 225000 | 9000 | 1977 | 2002 | 2019: 225000 | 225000
Electrical work - docks | 10 | 2000 | 200 |  |  | 2019: 1000; 2020: 1000 | 2000
Floats and hardware | 20 | 185000 | 9250 | 2011 | 2031 | 2024: 7000; 2027: 11000; 2028: 8000 | 26000
23 Mooring balls | 10 | 6900 | 690 | 2017 | 2027 | 2027: 6900
FUEL SYSTEM
Replace fixed fuel lines | 25 | 50000 | 2000 |  |  | 2024: 50000
Sumps. hose reels and flexible fuel lines | 10 | 10000 | 1000 | 2014 | 2024 | [10 empty] | 0
Fuel Tanks (double price from 1990) | 30 | 100000 | 3333.3333 | 1994 | 2024 | 2024: 100000
Fuel Pump (dockside) | 25 |  | 0
Fuel Inspection | 1 |  | 0
LAUNCHES
Re-power 2 launches | 10 | 30000 | 3000 | 2017 | 2027 | 2027: 35000 | 35000
Replace launch(es) each | 25 | 50000 | 2000 | 2017 | 2042
TOTAL (CIP) |  |  | 49836.6667 |  |  | 239300 | 51000 | 12000 | 9000 | 24000 | 175000 | 51000 | 35000 | 70900 | 23000 | 519500
Funding Levels 1/10/2018 | [5 empty] | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
Savings (CIF) |  |  | 224000 |  |  | 4700 | -26300 | -18300 | -7300 | -11300 | -166300 | -197300 | -212300 | -263200 | -266200
*Life: Estimated life expectancy. May need adjustment |  |  |  | *Estimate: Estimated cost to replace, no inflation added in. May need adjustment
Annual: Annual CIF contribution based on costs and life expectancy |  |  |  | Replaced: Year the item was last replaced
2018 CIP/CIF PYC By-laws page BL-3
Article II - Board of Directors
Section 6
The Capital Improvement Committee (CIC), appointed by the Commodore in accordance with Section 1 and 2 above, shall develop a Capital Improvement Plan (CIP) to maintain the structural integrity of the Club’s property and equipment as required by Constitution Article IX, Section 3. The CIP shall cover a minimum period of ten years and be updated and posted annually. The CIP shall identify planned Capital Projects that would cost more than the Maintenance and Repair budget would normally cover. The CIP shall also provide for unexpected and unplanned maintenance/repair costs of up to ten thousand dollars. The Committee will submit a prioritized list of recommended Capital Projects, with cost estimates, for Board approval and funding authorization not later than the September Board of Directors Meeting. All Board approved and funded Capital Projects will be presented at the Annual Meeting for review and endorsement.
Section 7
The Capital Improvement Fund (CIF) shall be established within the Club’s accounting system for the purpose of funding current and future Capital Projects identified from the Capital Improvement Plan. The Board shall annually identify the dedicated fund source and the amount of these funds to be allocated to each approved Capital Project. Whenever the source of revenue is a Dues increase or bank financing, the provisions of Constitution Article XII and Section 1 above, shall apply. The financial status of the CIF and each Capital Project account shall be briefed at the Annual Meeting.
CIF Allocation |  | 2015 | 2016 | 2017 |  | 2019: 2018; 2020: 2019
Clubhouse** |  | 90000 | 130000 | 155000 |  | 2019: 155000
Docks |  | 30000 | 35000 | 40000 |  | 2019: 20000
Launch |  | 30000 | 35000 | -23000 |  | 2019: 5700
Misc |  | 12000 | 12000 | 12000 |  | 2019: 13000
Total |  | 162000 | 212000 | 184000 |  | 2019: 193700
Funding |  | 162000 | 50000 | 30000 |  | 2019: 30000
2005-05-23 | 25 | 22000 | 19 pilings replaced May 2005 southern yellow was used for at least $1000 each around $20,000
Expected life time is 25 years, that would be 2030
2014-05-17 |  | 13260 | Pilings
2015-05-29 |  | 18340 | Pilings
2017-05-30 |  | 20895 | Pilings
|  | 52495 | Total 2014 & 2015 Seems to be a 10 year life span?
2006-08-10 |  | 19006 | Float 6 & 7
2007-03-13 |  | 15000
2007-05-15 |  | 22224 | Custom Floats
2007-11-30 |  | 8000
2008-04-15 |  | 8000
2008-04-19 |  | 7785
2008-10-24 |  | 8352
2009-05-05 |  | 16703
2009-09-16 |  | 8256
2010-03-08 |  | 8000
2010-04-25 |  | 8512
2010-10-22 |  | 17400
2011-04-16 |  | 17400
2011-05-12 |  | 16650
2016-09-23 |  | 3995
|  | 185283 | Total

## CIP 2019 50K
PYC CAPITAL IMPROVEMENT PLAN 2019 - 2028 10 year plan - Very rough proposal 1/10/2019
$50K funding | Life* | Estimate* | Annual | Replaced | Next | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | TOTAL
BUILDING
Carpet downstairs | 5 | 3500 | 700 |  |  | 2019: 3500 | 3500
Heating and air conditioning | 20 | 20000 | 1000 |  |  | 2023: 20000 | 20000
Paint dinning room, kitchen ceiling, flooring | 10 | 12000 | 1200 |  |  | 2020: 12000; 2027: 8000; 2028: 4000 | 24000
Plumbing replacement (need survey) | 25 | 10000 | 400 |  |  | 2024: 10000 | 10000
Replace kitchen floor & update kitchen | 10 | 20000 | 2000 |  |  | 2024: 8000; 2025: 12000 | 20000
Replace refrigerator unit in shed & kitchen | 15 | 4000 | 266.6667 |  |  | 2023: 4000 | 4000
Replace freezer in shed | 15 | 3000 | 200 | 2018 | 2033 | 2028: 3000 | 3000
Repair sliding windows | 10 | 2000 | 200 |  |  | 2019: 2000 | 2000
Replace roof | 30 | 20000 | 666.6667 | 2005 | 2035 | 2026: 35000 | 35000
Replace windows dining | 20 | 18000 | 900 |  |  | 2027: 10000; 2028: 8000 | 18000
Replace water heater | 10 | 3000 | 300 | 2019 | 2029 | 2019: 3000 | 3000
Replace 2 doors - (dining) repair siding | 25 | 5000 | 200 |  |  | 2021: 5000 | 5000
Sub structure inspection* | 5 | 1000 | 200 |  |  | 2020: 1000; 2025: 1000 | 2000
Repairs to sub structure* | 10 | 10000 | 1000 |  |  | 2020: 10000; 2021: 5000; 2022: 6000 | 21000
Replace tables and chairs | 10 | 5000 | 500 |  |  | 2021: 2000; 2022: 3000 | 5000
Update all club lighting | 10 | 6000 | 600 |  |  | 2025: 6000 | 6000
Upgrade WiFi system | 10 | 2000 | 200 |  |  | 2020: 2000 | 2000
4 Moorings in front of Club (staples) | 10 | 18000 | 1800 | [12 empty] | 18000
East sea wall* | 25 | 25000 | 1000 |  |  | 2020: 25000 | 25000
North sea wall and pilings* | 25 |  | 0 | [12 empty] | 2500
Carpet upstairs | 10 | 2500 | 250 | [12 empty] | 2500
LANDSIDE (no projections)
DOCK SYSTEM
Replace dock pilings (with north sea wall?) | 10 | 53000 | 5300 | 2015 | 2025 | 2025: 32000
Install sacrificial slide boards on 24 pilings | 10 | 4800 | 480 |  |  | 2019: 4800
Replace pier pilings, decking, walkway (swag) | 25 | 225000 | 9000 | 1977 | 2002 | 2019: 225000 | 225000
Electrical work - docks | 10 | 2000 | 200 |  |  | 2019: 1000; 2020: 1000 | 2000
Floats and hardware | 20 | 185000 | 9250 | 2011 | 2031 | 2024: 7000; 2027: 11000; 2028: 8000 | 26000
23 Mooring balls | 10 | 6900 | 690 | 2017 | 2027 | 2027: 6900
FUEL SYSTEM
Replace fixed fuel lines | 25 | 50000 | 2000 |  |  | 2024: 50000
Sumps. hose reels and flexible fuel lines | 10 | 10000 | 1000 | 2014 | 2024 | [10 empty] | 0
Fuel Tanks (double price from 1990)* | 30 | 100000 | 3333.3333 | 1994 | 2024 | 2024: 100000
Fuel Pump (dockside)* | 25 |  | 0
Fuel Inspection | 1 |  | 0
LAUNCHES
Re-power 2 launches | 10 | 30000 | 3000 | 2017 | 2027 | 2027: 35000 | 35000
Replace launch(es) each | 25 | 50000 | 2000 | 2017 | 2042
TOTAL (CIP) |  |  | 49836.6667 |  |  | 239300 | 51000 | 12000 | 9000 | 24000 | 175000 | 51000 | 35000 | 70900 | 23000 | 519500
Funding Levels 1/10/2018 | [5 empty] | 20000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
Savings (CIF) |  |  | 224000 |  |  | 4700 | 3700 | 41700 | 82700 | 108700 | -16300 | -17300 | -2300 | -23200 | 3800
*Life: Estimated life expectancy. May need adjustment |  |  |  | *Estimate: Estimated cost to replace, no inflation added in. May need adjustment
Annual: Annual CIF contribution based on costs and life expectancy |  |  |  | Replaced: Year the item was last replaced |  | 2025: * Needs better estimates
2018 CIP/CIF PYC By-laws page BL-3
Article II - Board of Directors
Section 6
The Capital Improvement Committee (CIC), appointed by the Commodore in accordance with Section 1 and 2 above, shall develop a Capital Improvement Plan (CIP) to maintain the structural integrity of the Club’s property and equipment as required by Constitution Article IX, Section 3. The CIP shall cover a minimum period of ten years and be updated and posted annually. The CIP shall identify planned Capital Projects that would cost more than the Maintenance and Repair budget would normally cover. The CIP shall also provide for unexpected and unplanned maintenance/repair costs of up to ten thousand dollars. The Committee will submit a prioritized list of recommended Capital Projects, with cost estimates, for Board approval and funding authorization not later than the September Board of Directors Meeting. All Board approved and funded Capital Projects will be presented at the Annual Meeting for review and endorsement.
Section 7
The Capital Improvement Fund (CIF) shall be established within the Club’s accounting system for the purpose of funding current and future Capital Projects identified from the Capital Improvement Plan. The Board shall annually identify the dedicated fund source and the amount of these funds to be allocated to each approved Capital Project. Whenever the source of revenue is a Dues increase or bank financing, the provisions of Constitution Article XII and Section 1 above, shall apply. The financial status of the CIF and each Capital Project account shall be briefed at the Annual Meeting.
CIF Allocation |  | 2015 | 2016 | 2017 | 2018 | 2019: 2019
Clubhouse** |  | 90000 | 130000 | 155000 | 155000
Docks |  | 30000 | 35000 | 40000 | 20000
Launch |  | 30000 | 35000 | -23000 | 5700
Misc |  | 12000 | 12000 | 12000 | 13000
Total |  | 162000 | 212000 | 184000 | 193700
Funding |  | 162000 | 50000 | 30000 | 30000
2005-05-23 | 25 | 22000 | 19 pilings replaced May 2005 southern yellow was used for at least $1000 each around $20,000
Expected life time is 25 years, that would be 2030
2014-05-17 |  | 13260 | Pilings
2015-05-29 |  | 18340 | Pilings
2017-05-30 |  | 20895 | Pilings
|  | 52495 | Total 2014 & 2015 Seems to be a 10 year life span?
2006-08-10 |  | 19006 | Float 6 & 7
2007-03-13 |  | 15000
2007-05-15 |  | 22224 | Custom Floats
2007-11-30 |  | 8000
2008-04-15 |  | 8000
2008-04-19 |  | 7785
2008-10-24 |  | 8352
2009-05-05 |  | 16703
2009-09-16 |  | 8256
2010-03-08 |  | 8000
2010-04-25 |  | 8512
2010-10-22 |  | 17400
2011-04-16 |  | 17400
2011-05-12 |  | 16650
2016-09-23 |  | 3995
|  | 185283 | Total

## Expenses
Ballpark breakdown of where the membership dues go (though not really accurate)
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12
PYC Expenses (most of it) |  | 2017 |  |  |  |  | 2018
|  |  | Dues Breakdown | With Depreciation
| Dollars | % | 100% | 81.2% |  | Dollars | %
Repairs and Maintenance | 19191 | 7.1% | 46.1484 | 39.1893
Utilities | 9430 | 3.489% | 22.6762 | 19.2567
Payroll | 116183 | 42.98% | 279.3842 | 237.2534
Property Tax | 17783 | 6.579% | 42.7626 | 36.3141
Insurance | 25789 | 9.541% | 62.0146 | 52.6629
Stipends | 3000 | 1.11% | 7.2141 | 6.1262
Accounting | 2005 | 0.7418% | 4.8214 | 4.0943
Workmans Comp | 2639 | 0.9763% | 6.346 | 5.389
Misc | 21730 | 8.039% | 52.2539 | 44.3741
Moorings | 22555 | 8.344%
CIF | 30000 | 11.1% | 72.1407 | 61.262
Total | 270305 | 84.92% | 523.6215 | 444.66
Depreciation | 48000 | 15.08% |  | 98.0192
Total Expenses | 318305
Dues active member | 650
CIF/CIP past funding | 30000 |  | 120.9677
CIF/CIP 100% funding | 50000 |  | 201.6129
Income (most of it)
Members Dues | 161200 | 55%
Application Fees | 5850 | 1.996%
Locker Rentals | 3690 | 1.259%
Slip Rentals | 41610 | 14.2%
Dinghy Fees | 2100 | 0.7165%
Launch Fees | 6420 | 2.191%
Club Rental | 2600 | 0.8871%
Moorings | 16403 | 5.597%
Fuel | 53210 | 18.16%
Total | 293083